## Slide 1: Theory of Change and Monitoring, Evaluation and Learning Plan

## Slide 2: Theory of Change

## Slide 3: Theory of Change
Sitting above the theory of change is the Council vision:
“Cumberland Council takes a fresh approach to the delivery of inclusive services that are shaped by our residents and communities. By enabling positive outcomes for health and wellbeing, prosperity and the environment we will fulfil the potential of our people and our area”.
Underpinning the theory of change are the Council values:
“Compassionate, innovative, empowering, ambitious, collaborative”.

## Slide 4: Logic or assumption?
Logic or assumptions connects each part of the theory of change. Evidence of the plausibility of this logic can largely be found in the Business Plan.
One assumption stands out as a significant risk to the project: Council staff have the time capacity to engage in evidence, evaluation, research and learning.
The HDRC needs to find ways to assure themselves that staff will be able to engage.

## Slide 5
Limited use of evidence and research in CC, but good commitment and buy in to the HDRC, a strong voluntary sector and new opportunities (e.g. Pears Cumbria Medical School).
A coastal, rural and dispersed range of communities with health inequalities.
ACTIVITIES
CONTEXT
Recruitment
Alliance building
HDRC governance and knowledge exchange
Council Research Governance Framework
Training and capability development
Community engagement and empowerment
Communication and dissemination
Research, evidence, evaluation and learning
Evaluation and sustainability
INPUTS
MECHANISMS OF CHANGE
OUTPUTS
SHORT TERM OUTCOMES
LONG TERM OUTCOMES
AIM
An evidence and research informed Council who can enable health and wellbeing for all residents.
Accessible
Relational
Transparent
Facilitative
Supportive
Approachable
Evidence informed
£4.8 million of NIHR funding over 5 years, creating 13 FTE HDRC posts
Partnerships and networks
Council staff capacity
Additional research funding secured
No. of staff
No. partnerships and networks
No. of meetings and reports
Governance framework
Audit, capability framework, no. of programmes, resource hub, no. of learners, no. dissertations, placements, secondments.
No. of meetings
PICE Framework
No. of co-designed projects
Priorities, gap analysis, research plan
Register , pipeline and evidence hub
No. submitted / successful funding bids
No. of REEL completed.
No. of communications and events
Sustainable business plan
HDRC delivered
Increased capacity and expertise
HDRC delivered
High quality, ethical REEL
Clear and accessible REEL process
Increased REEL capability in staff
Increased REEL confidence in staff
Council staff use evidence in decision making / planning
Increased REEL capability in community
Increase in community-led REEL
Council staff have access to evidence
Increased awareness of the HDRC
REEL continues beyond 2029
Evidence, evaluation, research and learning routinely generated in the Council
Evidence, evaluation, research and learning routinely used in the Council
Determinants of health systematically improved.
Notes: REEL = research, evidence, evaluation and learning from practice

## Slide 6: Activity / Workflow Details 1
Activity / Workstream | Details
Recruitment | Core staff Advisory staff Community researchers
Alliance building | Council directorates and elected members, HEI’s and VCS partners and wider research networks Engagement with Senior Leadership Team and Health and Wellbeing Board Cumbria Research Forum established with partners
HDRC Governance and Knowledge Exchange | Oversight, academic partnership, advisory panel meetings and ops meetings established with terms of reference HDRC reporting structures and protocols embedded
Council Research Governance Framework | Key definitions established, flow chart, procedures, policy. Evidence embedded in report and decision making templates. Assessment for health inequalities in directorate provision and commissioning.
Training and Capability Development | Annual skills audit, capabilities framework, training programme Directorate researcher roles and internships Secondments and placements Research resource hub Community capacity development HI and DoH training in universities.

## Slide 7: Activity / Workflow Details 2
Activity / Workstream | Details
Community engagement and empowerment | Establish Cumberland Community Advisory Group with MOU and ToR Develop a Cumberland Framework / Strategy for PICE Community Advisory Group co-design, co-produce and co-deliver research priorities and research
Research, Evidence, Evaluation and Learning (REEL) | Create a research register / pipeline and evidence hub Complete funding applications Dissertations from university students Literature reviews Service evaluations Evidence summaries Publications Novel research specific to Cumberland
Communication and dissemination | Communication and dissemination plans Website and social media Yearly dissemination and annual event
Evaluation and future sustainability | Annual evaluation with success measures, and impact measures Review of HDRC plan and design for next 5 – 10 years Income pipeline.

## Slide 8: Monitoring, Evaluation and Learning Plan

## Slide 9: Evaluation questions arising from the TOC
Context – is this truly the context we are working within?
Inputs – have these been fully invested / provided?
Activities – have these been delivered?
Mechanisms of change – have the team delivered the project in these ways?
Outputs – have the outputs been achieved?
Short term outcomes – have the outcomes been achieved and what impact do these have for beneficiaries?

## Slide 10: Monitoring v Evaluation Activity
ME | Component of TOC | Examples
Monitoring | Inputs | Budget use Additional resources from partners Wider funding secured
 | Activities | Gantt chart of workflows
 | Outputs | Number of training opportunities created Number of learners engaging
Evaluation | Mechanisms of change | Annual staff survey to understand whether the team are working in this way
 | Outcomes | Annual staff survey to assess skills, experience and knowledge Training evaluation forms

## Slide 11
TOC component | Output Indicator | Outcome indicator | Data collection tool | Data collector | Storage | Analytical approach | Analyst
Inputs | Budget monitoring |  | Budget changes over time | KS | Finance folder and KPI sheet | Variance | KS
Activities – Recruitment | Recruitment KPI |  | No of staff FTE | KS | Recruitment folder and KPI sheet | Count | KS
Activities - alliances | Networks KPI |  | No of partners | BC | Stakeholder sheet and KPI sheet | Count | BC
Activities – training | No of modules delivered No of participants | Participant feedback | Eventbrite Eventbrite MSForms | JLD | Training folder and KPI sheet | Count Count Percentage positive | JLD
Activities – community engagement and empowerment | No of co-researchers and co-designed research projects | Participant feedback | Community research plans MSForms | BC | Community folder and KPI sheet | Count Percentage positive | BC
Activities - research | No of projects registered No of outputs No of grants | No of decisions made with evidence | Pipeline sheet Evidence hub / research fish Grant income | DG | REEL folder and KPI sheet | Count Count Count Count | DG
Activities - Comms | Sign up to newsletters Followers on LinkedIn Attendees at annual event Press coverage | Participant feedback | Mailchimp LinkedIn Event planning and eval No of press items | SC | Comms folder and KPI sheet | Count Count Percentage positive | SC
HDRC Monitoring and Evaluation Plan

## Slide 12: Learning
Monitoring reports will be presented to the Oversight Board every two months based in our list of key performance indicators.
An evaluation will be conducted annually and reported to the end of year Oversight Board.
The Oversight Board and sub-groups will continually reflect and learn from the insights gained from the monitoring and evaluation activities ensuring continuous quality improvement.